## Backlog
ID | Milestone | Epic | Title | Type | Impl Model | Impl Model Reason | Review Model | Review Model Reason | Dependencies | Status | Assignee | Notes
M0-T1 | M0 Engineering foundation | M0-E1 Workspace & quality gates | Repo & workspace scaffolding | Ticket | Sonnet | Routine tooling/config; no domain logic or data-integrity risk | Sonnet | Low blast radius; check boundary lint + reproducibility | ADR-002 (closed 2026-09-03) | Done - accepted & merged 2026-09-03 | Sonnet worker / Sonnet reviewer | Review: PASS WITH FIXES (.gitattributes + release-age comment); fixes applied & re-verified at acceptance
M0-T2 | M0 Engineering foundation | M0-E1 Workspace & quality gates | CI pipeline & quality gates | Ticket | Sonnet | Standard CI config from stock actions; verified by deliberate-failure branches | Sonnet | Self-demonstrating acceptance criteria; check gate coverage + protection checklist | M0-T1 (done); GitHub remote (done) | Done - accepted & merged 2026-09-08 | Sonnet worker / Sonnet reviewer | Review: PASS no fixes (runs re-verified via Actions API); deviation (pnpm version pinning) architect-approved; branch protection = owner checklist pending
M1-T1 | M1 Domain + inventory ledger | M1-E1 Deterministic domain package | Inventory ledger core | Ticket | Opus | Highest-risk domain work: ledger/reconciliation math + idempotency + immutability | Opus | INV-LEDGER-1..4 are permanent guarantees; adversarial review of derivation/replay/negative-qty | M0-T1 (done) | Done - accepted & squash-merged 2026-09-08 | Opus worker / Opus reviewer (architect-dispatched) | Review: PASS after one fix round (forged-flag + rehydration trust closed; mutation-proven); 75 tests; handoff docs/handoff/M1-T1.*
M1-T2 | M1 Domain + inventory ledger | M1-E1 Deterministic domain package | Postgres schema & migrations (identity/household/inventory) | Ticket | Opus | Sensitive schema for inventory history; append-only enforcement; tenancy/RLS | Opus | Isolation + append-only guarantees must survive adversarial review; migration reversibility | M1-T1 (done); D-007 | Done - accepted & squash-merged 2026-09-10 - MILESTONE 1 COMPLETE | Opus worker / Opus reviewer (architect-dispatched) | Review: PASS after one fix round (INV-LEDGER-4 fail-open + unique-index oracle closed; worker self-found CREATE ROLE race); 96 DB tests; ADR-003 DECIDED
M1-T3 | M1 Domain + inventory ledger | M1-E1 Deterministic domain package | Units & quantity model | Ticket | Sonnet | Pure well-specified conversion functions with strong property tests | Opus | INV-SHOP-1 + nutrition math sit on this; silent conversion errors would corrupt inventory arithmetic | M0-T1 (done) | Done - accepted & squash-merged 2026-09-09 | Sonnet worker / Opus reviewer (architect-dispatched) | Review: PASS after one fix round (ground-truth factor pins added; makeBridge/alias/comparator defects closed); 150 tests
M1-T4 | M1 Domain + inventory ledger | M1-E1 Deterministic domain package | Allergen rule engine (deterministic) | Ticket | Opus | Safety-critical allergen enforcement (rule-23 high-risk list) | Opus | Adversarial review required (INV-ALRG-1/2); try to slip inputs past the screen | M0-T1 (done); fixtures from M1-T5 (done) | Done - accepted & squash-merged 2026-09-10 | Opus worker / Opus reviewer (architect-dispatched) | Review: PASS after one fix round (3 fail-open paths to ALLOWED closed; mutation-pinned); 163 tests; policies D-017
M1-T5 | M1 Domain + inventory ledger | M1-E2 Product knowledge foundations | Product lookup port + fixture adapter + coverage research spike | Ticket | Sonnet | Adapter interfaces + fixture plumbing + read-only research script | Sonnet | Check port-boundary hygiene (no vendor types; provenance present) + research method | M0-T1 (done) | Done - accepted & squash-merged 2026-09-09 | Sonnet worker / Sonnet reviewer (architect-dispatched) | Review: PASS after doc-only fixes; R-1 delivered; ADR-006 -> PROPOSED; 216 tests
M1-T6 | M1 Domain + inventory ledger | M1-E3 Foundation follow-ups (D-018) | Allergen screening: malformed allergen containers fail closed (pre-M4 gate a) | Ticket | Opus | Allergen enforcement (rule-23 list); closes a fail-open path to ALLOWED | Opus | Adversarial: try to reach ALLOWED with malformed data under a valid declaration | M1-T4 (done) | Done - accepted & squash-merged 2026-09-14 | Opus worker / Opus reviewer (architect-dispatched) | Review: PASS no fixes (488 probes + 4500 fuzz runs; 0 leaks); +136 tests; pre-M4 gate (a) closed; D-018 batch item 1 of 5
M1-T7 | M1 Domain + inventory ledger | M1-E3 Foundation follow-ups (D-018) | Correction-rate telemetry: SQL view + read function (north-star KPI) | Ticket | Sonnet | Read-only view + repository read; metric definition fixed in ticket | Opus | Tenancy (security_invoker view; ADR-003 rule 3) + exact KPI counting | M1-T2 (done) | Done - accepted & squash-merged 2026-09-14 | Sonnet worker / Opus reviewer (architect-dispatched) | Review: PASS no fixes (16 tenancy probes on real Postgres; 9 mutations); 625 tests w/ DB; KPI definition in ARCHITECTURE s8; D-018 batch item 2 of 5
M1-T8 | M1 Domain + inventory ledger | M1-E3 Foundation follow-ups (D-018) | Lot-selection policy for consumption (FEFO/FIFO planner) | Ticket | Opus | Inventory arithmetic splitting a decrease across lots (rule-23 list) | Opus | Probe ordering ties; undated/expired lots; exhaustion; reserved-key namespace | M1-T1 (done) | Done - accepted & squash-merged 2026-09-15 | Opus worker / Opus reviewer (architect-dispatched) | Review: PASS WITH FIXES (3 hand-built-input hardenings) -> re-review PASS; 17 mutations 15 killed; +35 tests; FEFO default PROPOSED (OQ-1); D-018 batch item 3 of 5
M1-T9 | M1 Domain + inventory ledger | M1-E3 Foundation follow-ups (D-018) | Ledger write retry helper (40001 + sequence-key 23505) | Ticket | Sonnet | Bounded retry wrapper with a precisely specified classifier | Opus | Concurrency-sensitive inventory updates; business conflicts must never be retried | M1-T2 (done) | Done - accepted & squash-merged 2026-09-15 | Sonnet worker / Opus reviewer (architect-dispatched) | Review: PASS WITH FIXES (pin assumeRole across retries) -> re-review PASS on real Postgres; no double-apply; 697 tests w/ DB; D-018 batch item 4 of 5
M1-T11 | M1 Domain + inventory ledger | M1-E3 Foundation follow-ups (D-018) | Ledger write path: aborted-transaction COMMIT silently discards work (pre-existing defect) | Ticket | Opus | Ledger write-path transaction semantics (rule-23 list) | Opus | Prove no rolled-back-but-reported-success outcome remains | M1-T9 (done); before M2 first write handler | Done - accepted & squash-merged 2026-09-16 | Opus worker / Opus reviewer (architect-dispatched) | Review: PASS WITH FIXES (pin fn-thrown-error rollback path; tenancy-leak mutant) -> re-review PASS; F4 repro 0 -> 1 durable row; 786 tests w/ DB
M1-T10 | M1 Domain + inventory ledger | M1-E3 Foundation follow-ups (D-018) | Maintenance bundle (11 accepted follow-ups a-k) | Ticket | Sonnet | Tooling pins fixtures and coverage items; small and mechanical | Sonnet | Per-item acceptance lines; no product-behaviour change; item (e) line-by-line | M1-T6; M1-T9 (runs last) | Done - accepted & squash-merged 2026-09-15 | Sonnet worker / Sonnet reviewer (architect-dispatched) | Review: PASS no fixes; all 13 items (a-m) landed; +71 tests (769 w/ DB); D-018 batch COMPLETE - engineering stopped for PO review
M3-E0-T1 | M3 Basic client (UI) | M3-E0 UX design gate | Prototype completion: missing MVP screens + non-happy states (docs only) | Ticket | Sonnet | HTML/CSS prototype work inside the token system; no product logic | Opus | Safety copy audit (nine rules; P11; three verdict states) | D-019 (done) | Done - accepted & squash-merged 2026-09-16 | Sonnet worker / Opus reviewer (architect-dispatched) | Review: PASS WITH FIXES (9 findings incl. skippable allergy gate; S5 ledger reconciliation + clamp sign) -> re-review PASS; 14 screens; Written 2026-09-15; S1/S2/S5/S9/S12 + recipe detail + states + legend/undo/who-did-what
M3-E0-T2 | M3 Basic client (UI) | M3-E0 UX design gate | Safety and provenance copy deck (docs only) | Ticket | Sonnet | Writing to a fixed rule set | Opus | Reviewed like code vs nine rules / D-017 / P11; coverage vs type unions | none (parallel with T1) | Done - accepted & squash-merged 2026-09-16 | Sonnet worker / Opus reviewer (architect-dispatched) | Review: PASS WITH FIXES (5 safety-wording defects + 9 smaller) -> re-review PASS; 63/63 codes; binding for M3 string table. Becomes the client string table for allergen surfaces
M3-E0-T3 | M3 Basic client (UI) | M3-E0 UX design gate | Token sheet: contrast measurements + scarcity audit (docs only) | Ticket | Sonnet | Measurement and tabulation | Sonnet | Check arithmetic; no token drift from prototype | M3-E0-T1 | Done - accepted & squash-merged 2026-09-16 | Sonnet worker / Sonnet reviewer (architect-dispatched) | Review: PASS WITH FIXES (5 uncovered contrast pairs) -> re-review PASS; 40 pairs; 16 FAILs w/ PROPOSED fixes (PO call); D-018a queue COMPLETE - stopped. Output docs/design/tokens.md ready for the typed token module in M3
M3-E0-T4 | M3 Basic client (UI) | M3-E0 UX design gate | Prototype v5: unknown-allergen commit moment, one consistent household, a11y remedies (docs only) | Ticket | Sonnet | HTML/CSS prototype work inside the token system | Opus | Allergen copy at the commit moment (rule 9 / rule 23) | none | Done - accepted & squash-merged 2026-10-08 | Sonnet worker / Opus reviewer (architect-dispatched) | Review: PASS WITH FIXES -> parallel fix passes merged -> re-check FAIL (focus halo) -> re-check PASS; PO approved v5 2026-10-08; squash 3069d8c; detector 124 -> 29
M2 | M2 Household + inventory API | - | Auth integration + household/inventory endpoints + isolation suite | Epic | TBD at ticketing | Authz/tenancy tickets expected Opus; CRUD wiring Sonnet | TBD at ticketing | Isolation tickets expected Opus review | M1 | Not started |  | Ticketed when M1 underway; contains cost-approval gates (auth vendor + PaaS)
M3-E0 | M3 Basic client inventory experience | - | UX design gate: wireframes + hi-fi mockups + safety-copy deck + validation | Epic | Sonnet-class design work | Design docs/mockups only - no code (PO directive 2026-09-10) | PO review | PO + Dean on-device review + hallway test are the review | M1 (done); design-direction + ux-plan docs | Ready - awaiting PO kickoff |  | Exit gate: PO sign-off + D-002 ratified before M3 build tickets exist
M3 | M3 Basic client inventory experience | - | Expo app: auth/household/inventory/barcode confirm flow | Epic | TBD at ticketing | Mostly UI/CRUD - expected Sonnet-heavy | TBD at ticketing | Sonnet expected; provenance-badge UX reviewed vs PRD | M2 | Not started |  | Correction-rate telemetry goes live here; GATED by new M3-E0 UX-design epic (docs/design/ux-plan.md) + D-002
M4 | M4 Barcode/product enrichment | - | Live lookup cascade + catalog merge + manual completion | Epic | TBD at ticketing | Normalization/merge tickets may escalate to Opus | TBD at ticketing | Per-ticket | M3; ADR-006 decision | Not started |  | Depends on R-1 coverage research outcome
M5 | M5 Receipt ingestion + confirmation | - | Fixture corpus + OCR pipeline + confirmation screen + dedupe | Epic | TBD at ticketing | Idempotent receipt processing tickets expected Opus | TBD at ticketing | Idempotency/dedupe tickets expected Opus review | M4; ADR-007 + ADR-009 decisions | Not started |  | Vendor bake-off (R-2); retention policy needs PO decision first
M6 | M6 Recipe generation + recommendations | - | LLM generation port + deterministic ranking + allergen screening | Epic | TBD at ticketing | Allergen-integration tickets Opus; prompt/adapter work Sonnet | TBD at ticketing | INV-ALRG E2E tickets expected Opus review | M3; M1-T4; ADR-005 vendor pick | Not started |  | Cost-approval gate for first LLM vendor
M7 | M7 Shopping-list closed loop | - | Gap computation + sharing + offline cache + close-the-loop | Epic | TBD at ticketing | Offline queue/conflict tickets expected Opus | TBD at ticketing | Sync/conflict tickets expected Opus review | M6 | Not started |  | Full MVP acceptance journey passes at exit
M8 | M8 Consumption + reconciliation | - | Meal logging decrements + expiration estimates + calorie display | Epic | TBD at ticketing | Decrement/reconciliation tickets expected Opus | TBD at ticketing | INV-MEAL-1/INV-NUTR-1 tickets expected Opus review | M7 | Not started
M9 | M9 Hardening & observability | - | Alerting + cost caps + security deep-set + deletion/export + legal gates | Epic | TBD at ticketing | Security/deletion tickets expected Opus | TBD at ticketing | Security tickets expected Opus review | M8 | Not started |  | Pre-launch legal gates R-3/R-4/R-5
M3-T1 | M3 Basic client inventory experience | M3 build (D-023) | Expo app scaffold, D-021 tokens, five-slot tab shell with Menu placeholder, fixture ApiClient | Ticket | Sonnet | Tooling and shell inside an established token system; no product logic | Sonnet | No rule-23 risk; token numbers, rule-11 dependencies, CI integration | M0-T1; M0-T2 (done) | Done - accepted & merged 2026-09-22 (11e79fb) | Sonnet worker / Sonnet reviewer | Review: PASS WITH FIXES (relative-path domain-boundary bypass) -> fix -> PASS
M2-T1 | M2 Household + inventory API | M2 (D-022 stubbed identity) | Identity port with fixture adapter, default-deny authorization, tenant-scoped sessions, GET /v1/inventory/items, redacted logging | Ticket | Opus | Household authorization and tenancy isolation (rule 23) | Opus | Adversarial: reach another household through every layer | M1-T2; M1-T9; M1-T11 (done) | Done - accepted & merged 2026-09-22 (079bfc1) | Opus worker / Opus reviewer / architect pass | Review: PASS WITH FIXES (compiled API could not start; 500 logging; production guard denylist) -> fixes -> architect F8 clean-state lint -> fix -> PASS
M3-T2 | M3 Basic client inventory experience | M3 build (D-023) | Onboarding S1 account + household and S2 allergies with the explicit-none gate, first-run routing guard, onboarding state behind the client port | Ticket | Sonnet | Screens inside the shell; a small gating state machine | Opus | Allergy gate is safety copy (P5, D-017) | M3-T1 (done) | Done - accepted & merged 2026-09-22 (2f44fb6) | Sonnet worker / Opus reviewer | Review: PASS WITH FIXES (copy scan blind to JSX; deep links bypassed the gate; Node globals leak; copy) -> fixes -> re-review found a stale-read redirect bounce -> fix -> PASS
M3-T3 | M3 Basic client inventory experience | M3 build (D-023) | Inventory list S4 and item detail S5 with ledger history, HttpApiClient read, correction/removal/undo behind the port | Ticket | Sonnet | Display of exact quantities and a fixture ledger | Opus | Ledger semantics on screen (rule 23) | M3-T1; M3-T2; M2-T1 (done) | Done - accepted & merged 2026-09-22 (b41b809) | Sonnet worker / Opus reviewer | Review: PASS WITH FIXES (non-discriminating float test; unreachable empty state; failed save reported success) -> fixes -> PASS
M2-T2 | M2 Household + inventory API | M2 (D-022 stubbed identity) | Inventory write endpoints (FEFO allocation, idempotent replay, undo), GET item detail, dev seed command | Ticket | Opus | Ledger writes, idempotency, concurrency, tenancy over writes (rule 23) | Opus | Adversarial: double-apply, cross-household, forged actor, partial commit, seed isolation | M2-T1; M1-T8; M1-T9; M1-T11; M3-T3 (done) | Done - accepted & merged 2026-09-22 (994d829) | Opus worker / Opus reviewer / architect pass | Review: PASS WITH FIXES (AJV stripped unknown fields; negative target minted a fake clamp) -> fixes -> PASS; 1559 tests with DB
M3-T4a | M3 Basic client inventory experience | M3 build (D-023) | Client plumbing: writes/detail/undo wired to M2-T2, UUIDv7 idempotency keys (expo-crypto), copy-deck §8 error strings, component test library, global toast host | Ticket | Sonnet | Wiring an existing port to existing endpoints | Sonnet | Key reuse on retry, error strings, component tests | M2-T2; M3-T3 (done) | Done - accepted & merged 2026-09-22 (0122ced) | Sonnet worker / Sonnet reviewer | Review: PASS (no code fixes); architect ruling adopted expo-crypto over a Math.random fallback -> PASS
M3-T4b | M3 Basic client inventory experience | M3 build (D-023) | Add food: S6 hub, S7 expo-camera scan, S8 confirm with the allergen row from engine-generated screening fixtures, S9 manual add, fixture lookup and createItem | Ticket | Sonnet | Screens plus one Expo module; no safety computation in the client | Opus | Scan-sheet allergen row is safety copy (P5, D-017, SR-1/SR-2) | M3-T4a (done) | Done - accepted & merged 2026-09-23 (62ef687) | Sonnet worker / Opus reviewer | Review: FAIL (hand-derived verdict ALLOWED where the engine says ALLOWED_WITH_UNKNOWNS) -> engine-generated fixtures with drift test, per-line rendering, 18 fixes -> PASS WITH FIXES (float guard, loading gate) -> PASS
M2-T3 | M2 Household + inventory API | M2 (D-022 stubbed identity) | Household create, join by code (migration 0008), members, item creation over the ledger | Ticket | Opus | Membership is the tenancy boundary (rule 23) | Opus | Adversarial: code brute force, join twice, create in a foreign household, replay | M2-T1; M2-T2; M3-T4b (done) | Done - accepted & merged 2026-09-29 (dcdd3cd) | - | M2-T4 (restrictions storage, product lookup endpoint, server-side screening) outlined, gated on A3
M3-T4c | M3 Basic client inventory experience | M3 build (D-023) | Web target for desk review, Expo start hygiene (EXPO_NO_TYPESCRIPT_SETUP), SDK-aligned safe-area-context and screens | Ticket | Sonnet | Tooling and dependency alignment; no domain logic | Sonnet | Verify clean tree after expo start and every screen on web from an empty build state | M3-T4b (done) | Done - accepted & merged 2026-09-24 (8620bb7); PO browser walk owed | Sonnet worker / Sonnet reviewer | Triggered by Andy's first local run: expo start rewrote tsconfig.json (breaks typecheck and format), w failed without react-native-web
M3-T5 | M3 Client (Expo) | M3 build (D-023 locked screens) | Shopping list S11: gap rows with origin chips, check-off with the close-the-loop prompt, in-session offline queue (fixture-backed) | Ticket | Sonnet | Screen inside the established shell and tokens; fixture data behind the port; no gap math in the client | Opus | Queued check-off replay is idempotency semantics (rule 23) and the loop Add writes a ledger row | M3-T4c (done) | Done - accepted & merged 2026-09-29 (dba4a7a) | - | Runs in parallel with M2-T3; D-024 rows 10 and 13 become a follow-up ticket if accepted
M2-T3a | M2 Household + inventory API | M2 (D-022 stubbed identity) | Hotfix: join-code rotation clock (transaction-start now() tripped the revoked-after-created check under concurrency in CI) | Ticket | Opus | Tenancy-adjacent DB write found red on main by CI | Opus | Same reviewer re-check of a two-file diff | M2-T3 (done) | Done - accepted & merged 2026-09-29 (3591bf8) | - | Deterministic two-connection reproduction added; clock_timestamp() for both stamps under the advisory lock
M2-T4a | M2 Household + inventory API | M2 (D-022 stubbed identity) | Product lookup over Open Food Facts (server-side), GET /v1/products/{code}, explicit not-run screening state on the scan sheet | Ticket | Opus | Data boundary the scan sheet trusts: provenance tiers | allergen tag mapping | external service failure modes | Opus | Adversarial: Known Fact leakage | absence-from-missing-data | 429 as not-found
M3-T4d | M3 Client (Expo) | M3 build (D-023 locked screens) | Client wiring to the M2-T3 endpoints: create household, join by code, household read, item creation over HTTP | Ticket | Sonnet | Client plumbing against existing endpoints (M3-T4a pattern) | Opus | Idempotent creation over the network and the create-or-join flow that picks the household | M2-T3 (done) | Done - accepted & merged 2026-09-29 (8d1217b) | - | Runs in parallel with M2-T4a; lookupProduct wiring is M3-T4e
M3-T4e | M3 Client (Expo) | M3 build (D-023 locked screens) | lookupProduct over HTTP and the scan sheet on live Open Food Facts data: nutrition basis, quantity tier, lookup refusals, package units, held key on S8 | Ticket | Sonnet | Client wiring plus fully specified rendering rules; one small adapter rule | Opus | First time live Estimated data reaches the add path: tier upgrades | nutrition basis | message leaks | double Save | M2-T4a and M3-T4d (done)
M3-T6 | M3 Client (Expo) | M3 build (D-023 locked screens) | Profile and household (S12): members with per-member allergy edit, join code for the owner, sign-out | Ticket | Sonnet | Screen reusing S2 components and existing endpoints | Opus | Allergy edit surface and an owner-only action | M3-T4d (done) | Done - accepted & merged 2026-09-30 (74371f1) | - | Batch A
M7-T1 | M7 Shopping-list closed loop | M7 | Shopping list persistence and endpoints: migration 0009, gap math on the server, check-off, add-to-inventory once per row, HTTP client wiring | Ticket | Opus | Rule-7 gap math, a PURCHASE ledger write, once-per-row idempotency | Opus | Adversarial: double add, cross-household, gap drift, replay conflicts | M2-T3 and M3-T5 (done) | Done - accepted & merged 2026-09-30 (01fca8a) | - | Batch A
R-6 | M8 Consumption + reconciliation | R (research) | Shelf-life data research: USDA FoodKeeper coverage, licence and the estimation rule (docs only) | Research | Sonnet | R-1 pattern: script, raw capture, findings | Sonnet | Licence and numbers reproduced | none | Dispatched 2026-09-29 | - | Batch A; no signup, no spend; feeds M8-T1
M2-T4b | M4 Barcode/product enrichment | M4 | Product lookup hardening: UPC-E, GTIN-14, English-name fallback, gluten tag mapping (D-026) | Ticket | Sonnet | Contained adapter and validator changes | Opus | Allergen map and code expansion decide what a scan resolves to | M2-T4a and M3-T4e (done) | Done - accepted & merged 2026-10-01 (a622495) | - | Batch A
M9-T0 | M9 Hardening | M9 | Maintenance bundle 2 (accepted follow-ups from the 2026-09-29 reviews) | Ticket | Sonnet | Small fully specified items | Sonnet | Nothing weakened | M2-T3a and M3-T4e (done) | Done - accepted & merged 2026-10-01 (86965b6) | - | Batch A
M9-D1 | M9 Hardening | M9 | Architecture documentation pass (docs only) | Docs | architect | rule 15 housekeeping | - | - | batch A merges | Done 2026-09-30 (architect) | architect | Batch A
BUG-002 | M9 Hardening | Bugs (PO device and browser tests) | API sends no CORS headers, web real mode blocked; fixed by the SK_CORS_ORIGINS allowlist (D-027) | Bug | Opus | Security boundary (browser origins) | Opus | Adversarial: leak with no allowlist | exact match | hook order | guard | none
BUG-001 | M3 Client (Expo) | Bugs (PO device and browser tests) | S2 Continue crashes with Maximum update depth exceeded (Android and web); root layout unmounted the navigator mid-navigation | Bug | Opus | Onboarding gate; allergy-gate bypass is the risk | Opus | Adversarial: bypass under the cover | redirect semantics | stale read | failed read | none
BUG-003 | M3 Client (Expo) | Bugs (PO device and browser tests) | Scan sheet under the Android navigation bar, camera panel too tall, list screens under the floating tab bar | Bug | Sonnet | Layout only | Sonnet | Insets and clearance pinned per screen | none | Fixed 2026-10-01 (88881e1) | - | Reported by Andy 2026-10-01
BUG-004 | M3 Client (Expo) | Bugs (PO device and browser tests) | Confirm on an AI proposal throws an uncaught rejection over the API (crash guard) | Bug | Sonnet | Error path only | Sonnet | Rejection handled, no unhandled promise | none | Fixed 2026-10-01 (523bbf2) | M2-T5 | Reported by Andy 2026-10-01
M2-T5 | M2 API | Inventory | Confirm an AI proposal over the API: endpoint, provenance confirmation, client wiring | Feature | Opus | AI output crossing into domain state; idempotency; tenancy | Opus | Adversarial: cross-household, double confirm, non-proposal | BUG-004 (client part) | Done 2026-10-01 (dab68f1) | - | From the 2026-10-01 device test
M3-T7 | M3 Client (Expo) | Inventory | Typed quantities on the S5 correction card and an editable package size on the S8 scan sheet | Feature | Sonnet | Inventory arithmetic through free text | Opus | Exact micros, tier flip pinned | BUG-003 | Done 2026-10-02 (7b73c0d) | - | Andy: 125 g vs 248 g, 500 taps
M2-T6 | M2 API | Inventory | Move an item between locations (D-024 row 1): migration 0010, endpoint, S5 action | Feature | Sonnet | Migration next to inventory history; household write | Opus | Ledger untouched by a move, idempotent | M3-T7 (S5 part) | Done 2026-10-02 (ada4455) | - | D-024 row 1 approved by Andy 2026-10-01
BUG-005 | M3 Client (Expo) | Bugs (PO device and browser tests) | Metro served the bundle before its index was ready: 34 agent worktrees in the watch folder; block list fix | Bug | Sonnet | Tooling config | Sonnet | Config test and smoke | none | Fixed 2026-10-03 (f8a5b51) | - | Reported by Andy 2026-10-02; cause: architect's unpruned worktrees
M2-T4c | M2 API | Product lookup | Send the scanned symbology with the lookup; GTIN14 port normalisation | Feature | Sonnet | Contract and route parsing | Sonnet | Hint only narrows | none | Done 2026-10-06 (c82a642) | - | M2-T4b follow-up (priority raised)
M3-T8 | M3 Client (Expo) | Test infrastructure | Lint block for app scripts; shared camera stand-in for the S7 gate tests | Chore | Sonnet | Tooling and tests | Sonnet | No assertion weakened | none | Done 2026-10-06 (0c4db1f) | - | BUG-001 follow-ups
M2-T7 | M2 API | Inventory | Lot label and quantity origin on item create | Feature | Sonnet | Small contract and service change | Opus | Idempotent replay comparison | M2-T4c | Done 2026-10-06 (9e41b98) | - | M3-T7 follow-up
M3-T9 | M3 Client (Expo) | Inventory | A passed best-by reads expired (D-030), S4 and S5 | Feature | Sonnet | Display-only helper and two screens | Sonnet | Not rule-23; provenance honesty of strings | none | Done 2026-10-07 (e944025) | - | Review PASS; follow-up: tomorrow reads use today
BUG-007 | M3 Client (Expo) | Bugs | Home header avatar clipped under the status bar | Bug | Sonnet | Small layout fix | Sonnet | Not rule-23 | none | Done 2026-10-07 (82a03a0) | - | Review PASS; follow-up: top inset on every screen
BUG-006 | M7 Shopping | Bugs | A checked shopping row shows 0 lb | Bug | Opus | Shopping gap read and PURCHASE path (rule 23) | Opus | Rule 23 | none | Done 2026-10-07 (c047edf) | - | Review PASS; architect code pass clean; PO question on two row display edge cases
M2-T8 | M2 API | Inventory | Count units take whole numbers only (D-029), client and server | Feature | Opus | Inventory arithmetic on every write path (rule 23) | Opus | Rule 23 | none | Done 2026-10-07 (f640e2c) | - | Review PASS WITH FIXES then PASS (Sonnet re-check); architect code pass clean
M9-T1 | M9 Hardening | Maintenance | CI red: pnpm audit on shell-quote and source-map-js | Maintenance | Sonnet | Transitive pins only | Sonnet | Tooling | none | Done 2026-10-07 (376f62b) | - | Review PASS; follow-up: drop the overrides when parents pull patched ranges
M9-T2 | M9 Hardening | Maintenance | COUNT unit aliases published from contracts with a consistency test | Maintenance | Sonnet | List move plus a test | Sonnet | Not rule-23 | none | Done 2026-10-07 (8948abb) | - | Review PASS WITH FIXES (format) then PASS
M3-T11 | M3 Client (Expo) | Inventory | A best-by one day out reads tomorrow; calendar-day counts | Feature | Sonnet | Display wording | Sonnet | Not rule-23 | none | Done 2026-10-07 (84af14b) | - | Sent back once (rolling 24h); review PASS WITH FIXES (format) then PASS; follow-up: printed best-by stored as UTC midnight
M3-T12 | M3 Client (Expo) | Inventory | One typed client ApiError; COUNT_NOT_WHOLE through ledgerErrorMessage | Maintenance | Sonnet | Client refactor | Sonnet | Not rule-23 | none | Done 2026-10-07 (d23a3c6) | - | Review PASS WITH FIXES (format) then PASS; follow-up: vitest dist and per-app run
M3-T10 | M3 Client (Expo) | Layout | Top safe-area inset on every screen | Bug | Sonnet | Layout only | Sonnet | Not rule-23 | M3-T12 | Done 2026-10-07 (c825350) | - | Review PASS; device pass owed on notched phones
M3-E0-T5 | M3 Client (Expo) | M3-E0 UX design | Prototype v6: Menu Plan ahead, diet picker, shopping origin band | Design | Sonnet | Prototype HTML with the impeccable skill | Opus | Diet and allergy copy side by side; gap shown as deterministic | none | Ready 2026-10-08 | - | From Dean 2026-10-07; D-024 partial ratification and D-031
M3-E0-T7 | M3 Client (Expo) | M3-E0 UX design | KitchenSmart design kit: DESIGN.md, light and dark token previews, README (from v6) | Design | Sonnet | Transcribe v6 values with the impeccable skill | Sonnet | No rule-23 surface; values and safety layer checked against v6 and D-021 | M3-E0-T6 | Ready 2026-10-14 | - | Andy request; impeccable detect QC on both previews; M3-T13 now depends on it